## Sheet1 (hidden)
Tasks | Duration | 12 Aug 2024 - 8 Sep 2024 |  |  |  | 9 Sep 2024 - 6 Oct 2024 |  |  |  | 7 Oct 2024 - 3 Nov 2024
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Set up user interface | 1 week | bar: 12 Aug 2024 - 8 Sep 2024 1
2. Test Motors and Size Battery | 2 weeks | bar: 12 Aug 2024 - 8 Sep 2024 1 to 12 Aug 2024 - 8 Sep 2024 2
3. Complete speed, direction control, and encoder setup | 2 weeks | bar: 12 Aug 2024 - 8 Sep 2024 1 to 12 Aug 2024 - 8 Sep 2024 2
4. Design arm and motor connector | 2 weeks | bar: 12 Aug 2024 - 8 Sep 2024 1 to 12 Aug 2024 - 8 Sep 2024 2
5. Modify and finalize frame design | 2 weeks | bar: 12 Aug 2024 - 8 Sep 2024 1 to 12 Aug 2024 - 8 Sep 2024 2
6. Setup RPI | 1 week | bar: 12 Aug 2024 - 8 Sep 2024 2
7. Program robot logic | 1 week | bar: 12 Aug 2024 - 8 Sep 2024 2
8. Procurement | 3 weeks | bar: 12 Aug 2024 - 8 Sep 2024 2 to 12 Aug 2024 - 8 Sep 2024 4
9. 3D Print connector for arm motor | 1 weeks | bar: 12 Aug 2024 - 8 Sep 2024 2
10. Program and integrate arms | 1 week | bar: 12 Aug 2024 - 8 Sep 2024 2
11. Program decision matrix | 3 weeks | bar: 12 Aug 2024 - 8 Sep 2024 3 to 9 Sep 2024 - 6 Oct 2024 5
12. Setup and Test Camera CV | 3 weeks | bar: 12 Aug 2024 - 8 Sep 2024 3 to 9 Sep 2024 - 6 Oct 2024 5
13. 3D Print Spring Holder and Foam Contacts | 1 weeks | bar: 12 Aug 2024 - 8 Sep 2024 3
14. Design and make mounting for electronics | 2 weeks | bar: 12 Aug 2024 - 8 Sep 2024 3 to 12 Aug 2024 - 8 Sep 2024 4
15. Assemble Frame | 2 weeks | bar: 12 Aug 2024 - 8 Sep 2024 4 to 9 Sep 2024 - 6 Oct 2024 5
16. Synchronize | 1 week | bar: 9 Sep 2024 - 6 Oct 2024 6
17. Wiring and Powering up the Robot | 1 week | bar: 9 Sep 2024 - 6 Oct 2024 6
18. Match Specifications, Test, and Troubleshoot | 3 weeks | bar: 9 Sep 2024 - 6 Oct 2024 7 to 7 Oct 2024 - 3 Nov 2024 9
19. Report and Slides for Submission | 3 weeks | bar: 7 Oct 2024 - 3 Nov 2024 10 to 7 Oct 2024 - 3 Nov 2024 12

## To Do 2025 Timeline
| June |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
| W3 | W4 | W1 | W2 | W3 | W4 | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Recess Week | Week 7, Examination Week | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Reading Week | Examination Weeks | W3 | W4
Research Arm Motor | June W3: Jeanette Elgin; June W4: Jeanette Elgin
Research Pose Estimation | June W3: Yogee; June W4: Yogee
Create Figma | June W3: Zakir; June W4: Zakir
Research on Jetson & ROS | June W3: Elgin; June W4: Elgin; July W1: Elgin; July W2: Elgin; July W3: Elgin; July W4: Elgin
Arm Prototype | July W1: Jeanette; July W2: Jeanette; July W3: Jeanette; July W4: Jeanette
Develop UI (without actuation) | July W1: Zakir; July W2: Zakir; July W3: Zakir; July W4: Zakir
Develop full pose estimation model |  |  | Yogee | Yogee | Yogee | Yogee | Yogee | Yogee | Yogee | Yogee
Enable Jetson to perform mechanical action | August Week 0: Elgin; August Week 1: Elgin
Develop UI (with actuation) | August Week 0: Zakir; August Week 1: Zakir
Develop Physical Arm | August Week 0: Jeanette; August Week 1: Jeanette; August Week 2: Jeanette; August Week 3: Jeanette
Integrate pose estimation to app | August Week 3: Yogee Zakir; September Week 4: Yogee Zakir; September Week 5: Yogee Zakir; September Week 6: Yogee Zakir
Integrate arm with Jetson (bare bones, disconnected from shoulder) | September Week 4: Elgin; September Week 5: Elgin
Design shoulder to integrate real sense, arm and screen | September Week 4: Jeanette; September Week 5: Jeanette; September Week 6: Jeanette |  |  | Jeanette
Change paddings of the robot | [15 empty] | Zakir | Zakir
PCB design | [15 empty] | Elgin | Elgin | Elgin | Elgin
Build shoulder | [16 empty] | Jeanette | Jeanette | Jeanette
Assemble upper | [19 empty] | Everyone | Everyone

## Task Description
Research Arm Motor | Research Pose Estimation | Research on Desktop App Development | Research on Jetson & ROS | Arm Prototype | Develop full pose estimation model | Develop UI | Enable Jetson to perform mechanical action | Develop Arm | Integrate pose estimation to app | Integrate arm with Jetson (bare bones, disconnected from shoulder) | Change paddings of the robot | Design shoulder to integrate real sense, arm and screen | Integrate app with Jetson | PCB design | Build shoulder | Assemble upper