## Sheet1
Week | Jeanette | Elgin | Zakir | Yogee
Week 1 12/1 - 18/1 | Finalised Design for Lower Mechanical Design - Procure screw jack (DONE) - Drawings consulted (graham -> patrick/central workshop) (semi-done) -> Drawings sent out to central workshop to fabricate *-> Finalise Design for Base Steel Plate & Platform Jack after screw jack motor arrives (measure dimension before confirming final dimension required for both parts). | - Draft power and data architecture for upper body system - Finalize arm CAD design accounting for shielding of gears and foam holder | - Reformat the GUI code for optimization (DONE) - Integrate Yogee's reaction time into the GUI (DONE) - Integrate Elgin's power performance into the GUI - CAD boxing gloves holder (DONE) - Build the Technique Correction GUI logic
Week 2 19/1 - 25/1 | Finalised Design for Component Holder - Head/Torso Contact Points - Screen Display - Guide Wheels + Handle | - Working prototype of arm (with motors and controller) with command control - Padding design with attachment and slot for IMU - Draft full upper torso design - Control | - Print out CAD boxing gloves holder - Build first hardware prototype for power performance - Build software to handle the punch detection as inputs (TBD; either for stamina or as literal inputs or both)
Week 3 26/1 - 1/2 | Assemble Lower Mechanical Design - Test stability of robot - Power & Control Test | Assemble Upper Mechanical Design - Test puch executions with software control (ros) - Validate data handling for motors and IMU | - Source for parts for Torso holder - CAD the final Torso Holder - Build the spar-training modes: Counter-Only Drill, Defence-Only Drill and Rhythm Change Drill
Week 4 2/2 - 6/2 | Improve design of robot - Quick fixes made before first user testing - Finalise design for: -- Rotation Mechanism -- Linear Mechanism (omitted; lack of budget/time) | - Final system calibration for user testing | - Assemble the Torso Holder - Build the coaching-training mode: Punch Callouts with Verification mode
PHASE 1 -- CDE Robotics & AI Fair 7/2 - 8/2 User Testing #1 | Full skeleton ready - Height Adjustment Feature works |  | -
Week 5 9/2 - 15/2 |  |  | -
Week 6 16/2 - 22/2 (17/2-18/2 CNY) |  |  | -
READING WEEK 23/2 - 1/3 |  |  | -
Week 7 2/3 - 8/3 |  |  | -
Week 8 9/3 - 15/3 |  |  | -
Week 9 16/3 - 22/3 |  |  | -
Week 10 23/3 - 29/3 |  |  | -
Week 11 30/3 - 5/4 (3/4 Good Friday) |  |  | -
Week 12 6/4 - 12/4 |  |  | -
Week 13 13/4 - 16/4 |  |  | -
PHASE 2 -- iDP Project Showcase 17/4 |  |  | -